## Clinic Contact List
Name | Phone Number | Email | Role | Notes
|  |  | IT Onsite Support | Contact for hospital IT onsite support
|  |  | IT Client/User List Creator | Individual resposnsible for sending the encrpyted lists to MOH
|  |  | IT Inventory Manager | Individual responsible for setting up inventory of the clinics
|  |  | Security | To have the ITS/Accenture and CompuCom resources get access passes, register, etc
|  |  | Main IT Stream Contact | Inidivudal that will reach out with any questions/concerns to Misbah or vice versa
|  |  | Facilities | Provide location for parking and address of clinic Provide PPE to support staff Provide wipes to clean iPads
|  |  | Logistics | Contact that will provide clinical schedule so we can schedule support staff accordingly
|  |  | Super Users | Support Clinic Users on use of COVAXON
|  |  | QA Lead | Monitor quality of data and correct errors
|  |  | Inventory Lead | Record receipt of inventory, waste and reconcile data
|  |  | Performance Lead | Ensure clinic operations is flowwing well, ensure guidance is adhered to, ensure proper monitoring of inventory and cold chain
Clinic Location/Address:
Vacciniation Clinic Address:

## Questions & Answers - Clinic
Questions | Example Response
Hosptial Name:
IT
Confirm if Internet availability has been tested and provide Hospital IT support contacts to PHS | Name: Email: Phone Number:
For creation of new users on the spot - identify the individual that willl be creating new users on the spot if necessary (e.g., head nurse/nurse manager) from each site | __________ will be in charge of creating new user on the spot, technical support by _________
Who will be responsible for printing AEFI forms on regular printers and ensure that forms are available at the appropriate areas (e.g., AEFI Monitoring room) | ___________will be in charge of printing AEFI forms Direct link to AEFI form below: https://www.publichealthontario.ca/-/media/documents/a/2020/aefi-reporting-form.pdf?la=en
Who should our IT team contact when they arrive at the vaccination clinic? | Name: Email: Phone Number:
Security
Who is in charge of providing security badges for external IT staff for clinic? | List of staff has been provided to ______
Will there be a Secure area at end of day for Ipads which will allow charging overnight? If so where? | We have lockable storage spaces right off the clinic space (gym). This room has a lot of available power. We will have additional power bars and shelving for the different units (iPad, laptops) We have 3 lockable storage spaces right off the clinic space (gym) and we have additional lockable rooms (recovery/rest) and respite spaces. There will be more than enough secure storage. Additionally, the clinic space (gym) is fully lockable and will be secured at the end of the day.
Is there any process MOH shold know about to obtain security clearance for external IT staff for clinic? | Provide List external IT support staff list to _________
Logistics
Please provide PHS Parking spaces, loading dock information | Please park in _______ and contact ________ who will provide parking passes
Please confirm clinic open and closed hours - **see Clinic hours tab | Clinic hours will be from ________ with the first available booking at _____ and last booking at _________ Operating ________ days per week.
Please Provide Clinic Location | Address:
Confirm location of locked storage room for end of day storage of clinic equipment | Confirmed - Locked storage room for IT equipment will be available and located ____________ and will be locked at the end of every vaccination day
Are clinics able to provide the wipes that they use to clean their surfaces to wipe the iPads down? | Confirmed - We are providing approved ___________ PPE Material. We have protective booths with upper plexiglass to protect the screeners. We have protective plexiglass screens to protect the registrars. All staff will be provided with face masks. All stations will have hand sanitizer and disinfectant wipes. Resource: ___________

## Clinical Hours Schedule
FOR THE WEEK OF: | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | SUN |  | MON |  | TUE |  | WED
2021-01-11 | 2021-01-11 |  | 2021-01-12 |  | 2021-01-13 |  | 2021-01-14 |  | 2021-01-15 |  | 2021-01-16 |  | 2021-01-17 |  | 2021-01-18 |  | 2021-01-19 |  | 2021-01-20 |  | 2021-01-21 |  | 2021-01-22 |  | 2021-01-23 |  | 2021-01-24 |  | 2021-01-25 |  | 2021-01-26 |  | 2021-01-27
Hospital Name | In | OUT | In | Out | In | Out | In | Out | In | Out | In | Out | In | Out | In | Out | In | Out | In | Out | In | Out | In | Out | In | Out | In | Out | In | Out | In | Out | In | Out
SAMPLE HOSPITAL | 12:00PM | 8:00PM | 12:00PM | 8:00PM | 12:00PM | 8:00PM | 12:00PM | 8:00PM | 12:00PM | 8:00PM | 12:00PM | 8:00PM | CLOSED |  | CLOSED |  | 12:00PM | 8:00PM | 12:00PM | 8:00PM | 12:00PM | 8:00PM | 12:00PM | 8:00PM | 12:00PM | 8:00PM | 12:00PM | 8:00PM | CLOSED |  | 12:00PM | 8:00PM | 12:00PM | 8:00PM

## Clinic Readiness Checklist
Clinic Readiness Check list
| Logistics | Done
1 | Is the clinic is near windows – good access points in/out for flow, signage, arrows, accessibility to washrooms
2 | Have you checked for enough outlets and that they are working
3 | Have you checked if there are enough Power bars/cords on site and available
4 | Is PPE available for IT staff (e.g., masks)
5 | Do you have enough office supplies such as pen, paper etc…
6 | Have you ensured clinic staff have a mobile phone and an organization email account (associated to the Hospital domain ie., toh.ca/uhn.ca etc.) and that they know their password ahead of time - for 2Factor authentication
7 | Extra staff for data entry in case there are delays and they have to shift to the checkout station being the data entry model
8 | Do you have sanitizers to wipe down equipment
9 | Confirm that check-in and check-out readiness (as per instructions/training) is completed ahead of time.
10 | Have you confirmed the number of staff operating the clinics per shift
11 | Have you confirned your clinic schedule at least 2 weeks in advance
12 | Have you determined your clinic model (stations or back-end data entry)
13 | Have your received the Clinic-in-a-Box equipment and has it been catalogued
14 | Have you sent the confirmed inventory catalogue to the ministry
15 | Is more equipment required and has this requirement been communicated to the ministry (with a 7-day lead time)
16 | Have you tested all equipment to ensure in good working order and have you communicated to ministry any issues
17 | Have your clinic leads been identified (IT, Super Users, QA, Performance, Inventory)
18 | Have you provided the required user list information to the ministry
19 | Have you communicated to staff what is expected (ex. They will receive an email from Salesforce for account setup) and who to go to if there are issues (Site Super User then Ministry Help Desk)
20 | Have you communicated to clinets to bring their health card
21 | Have you determine who should have access to dashboard data
22 | Have you rehearsed a plan if technology is not available
23 | Have you arranged for extra staff for data entry in case there are delays and they have to shift to the checkout station being the data entry model
24 | Does your facility have capacity to manage logistical planning and implementation requirements for on-site immunizations?
25 | Do you have nursing staff available to administer vaccines to your residents?
26 | Do you have an existing influenza immunization strategy you could mirror for COVID-19 vaccine administration within your facility?
27 | Do you have a refrigeration unit to safely store vaccines that has passed York Region Public Health’s cold chain maintenance inspection in which to store the vaccine in the required +2°C to +8°C range?
28 | Do you have a secure room with restricted access in which to store vaccine?
29 | Does your facility meet the COVaxON documentation system requirements listed below?
| Technology | Done
1 | Ensure Equipment are labeled and provide instructions on what to do for inventory management
2 | Check Internet connectivity using hubs
3 | Turn on IPAds to charge and test connectivity and ensure there is sufficent process/time for allowing equipment to recharge
4 | If your clinic is using your own supplied computers - make sure the laptops meet the following requirements/specifications (1)At least 5 GB of RAM with 2 GB available for Salesforce browser tabs (2)Latest OS: Windows 10 and/or MACOS with appropriate browser. (ie. Chrome preferred) (3)up to date with security patches (4)To be used on safe and secure hospital network (not outside i.e. public) (5) The computer/laptop/asset is managed by the hospital IT and on radar for their cyber security (with all required controls in place) (6) Computer connected to broadband internet (7) Network latency of 200 ms or less (8) Download speed of 1 Mbps or greater
5 | Ensure your Laptop browsers meet the following specifications (1) MICROSOFT® EDGE CHROMIUM - Supports latest stable browser version 87 (2) GOOGLE CHROME™ - Supports latest stable browser version 87 (3) MOZILLA® FIREFOX® - Supports latest stable browser version min 84 (4) APPLE® SAFARI - Supports latest browser stable version
6 | If the printers that are used is not part of clinic in a box (1) make sure it is set to print ~3x4” to print out receipts, if required for physical resident files and for retirement home clients (2) ensure that iPADS/laptops can connect to the new printers
7 | Keyboards for the check in and check out staff
8 | Determine and let PHS who should have access to dashboard data
| Security/Facilities | Done
1 | Security badges for IT staff
2 | Name tags for offsite staff
3 | Locked/secure storage area for IT equipment (e.g., IPADS/Printers) during off hours
4 | Provide MOH a site security contact so that external onsite support can get the proper security badges/clearance
| Materials Required | Done
1 | Print out AEFI forms and ensure forms are available in AEFI mointoring room Latest AEFI Forms can be found here: https://www.publichealthontario.ca/-/media/documents/a/2020/aefi-reporting-form.pdf?la=en
2 | Print out consent forms for backup and ensure printed forms/receipts are in the appropriate rooms (e.g., vaccination/check in area) *Recommendation: print these in different colour paper which helps differentiate for patients Consent Form print is located here: https://ontariogov.sharepoint.com/sites/PHS/COVAX/Forms/AllItems.aspx?csf=1&web=1&e=hBWJfA&cid=8450794e%2Df3d6%2D4d7b%2D8625%2D23f33de1ec39&FolderCTID=0x01200094856F5D12B0BD4CA6F5A8B7FBB7F237&viewid=f7a095b9%2D2c1e%2D4ed0%2D89df%2D5eeac86e9ff2&id=%2Fsites%2FPHS%2FCOVAX%2FCOVaxon%20Information%20Package%20%2D%20Hospital%2FConsent%2FConsent%20form
3 | Print out receipt form for backup and ensure printed receipts are in the appropriate rooms (e.g., checkout area)*Recommendation: print these in different colour paper which helps differentiate for patients Receipt print out templates is located here: https://ontariogov.sharepoint.com/sites/PHS/COVAX/Forms/AllItems.aspx?csf=1&web=1&e=hBWJfA&cid=8450794e%2Df3d6%2D4d7b%2D8625%2D23f33de1ec39&FolderCTID=0x01200094856F5D12B0BD4CA6F5A8B7FBB7F237&viewid=f7a095b9%2D2c1e%2D4ed0%2D89df%2D5eeac86e9ff2&id=%2Fsites%2FPHS%2FCOVAX%2FCOVaxon%20Information%20Package%20%2D%20Hospital%2FTechnology%20Back%20up%20Solution
| System access and training readiness | Done
1 | Ensure that the appropriate users have access to the training materials provided on sharepoint Latest training materials can be found here: https://ontariogov.sharepoint.com/sites/PHS/COVAX/Forms/AllItems.aspx?csf=1&web=1&e=hBWJfA&cid=8450794e%2Df3d6%2D4d7b%2D8625%2D23f33de1ec39&FolderCTID=0x01200094856F5D12B0BD4CA6F5A8B7FBB7F237&viewid=f7a095b9%2D2c1e%2D4ed0%2D89df%2D5eeac86e9ff2&id=%2Fsites%2FPHS%2FCOVAX%2FCOVaxon%20Information%20Package%20%2D%20Hospital%2FTraining%20Material
1.1 | Let PHS (Sergiu/Carmen) know the users that will require access to Sharepoint (for latest training materials/templates/COVax info package)
2 | Ensure at least one staff has a COVAX Site Superuser role assigned and they are trained on how to load client data front end
3 | Ensure at lease one staff has COVAX Inventory Manager role assigned and they are trained to load inventory data
4 | Ensure Clinic staff have their own mobile phones that will need to be used for 2 factor Authentication Two-factor authentication: (1) A smart phone is needed to download the Salesforce Authenticator app (2) The same phone will be required to obtain codes to access the application
4.1 | Refer to instructions/PDF (ahead of time) on how to complete two step SF verification from user’s cell phone Salesforce Authenticator app instructions are located here: https://ontariogov.sharepoint.com/sites/PHS/COVAX/Forms/AllItems.aspx?csf=1&web=1&e=hBWJfA&cid=8450794e%2Df3d6%2D4d7b%2D8625%2D23f33de1ec39&FolderCTID=0x01200094856F5D12B0BD4CA6F5A8B7FBB7F237&viewid=f7a095b9%2D2c1e%2D4ed0%2D89df%2D5eeac86e9ff2&id=%2Fsites%2FPHS%2FCOVAX%2FCOVaxon%20Information%20Package%20%2D%20Hospital%2FTechnology%20Set%20up%20Instructions
5 | Complete client upload template and ensure instructions to upload and collect data are followed and get confirmation Client templates has been received latest Client upload template can be found here: https://ontariogov.sharepoint.com/sites/PHS/COVAX/Forms/AllItems.aspx?csf=1&web=1&e=hBWJfA&cid=8450794e%2Df3d6%2D4d7b%2D8625%2D23f33de1ec39&FolderCTID=0x01200094856F5D12B0BD4CA6F5A8B7FBB7F237&viewid=f7a095b9%2D2c1e%2D4ed0%2D89df%2D5eeac86e9ff2&id=%2Fsites%2FPHS%2FCOVAX%2FCOVaxon%20Information%20Package%20%2D%20Hospital%2FUpload%20Templates%2FTemplates%20for%20PC%2FClient
6 | Complete user upload template and ensure instructions to upload and collect data are followed and get confirmation User templates has been received latest User upload template can be found here: https://ontariogov.sharepoint.com/sites/PHS/COVAX/Forms/AllItems.aspx?csf=1&web=1&e=hBWJfA&cid=8450794e%2Df3d6%2D4d7b%2D8625%2D23f33de1ec39&FolderCTID=0x01200094856F5D12B0BD4CA6F5A8B7FBB7F237&viewid=f7a095b9%2D2c1e%2D4ed0%2D89df%2D5eeac86e9ff2&id=%2Fsites%2FPHS%2FCOVAX%2FCOVaxon%20Information%20Package%20%2D%20Hospital%2FUpload%20Templates%2FTemplates%20for%20PC%2FUser
7 | Make sure the backup template (doses) is available and staff instructed on how to use it
8 | Confirmation that all clinic roles and users have completed required training ahead of the clinic day.
9 | Inform PHS (Misbah/Carmen) of your clinical hours/Vaccination start date
User email: (1) For registering to COVaxON Service the user needs to provide an email ID (affiliated to their organization/corporation is preferred) (2) did Account creation email come from an identified/authorized site contact with information to create an account on Salesforce (COVaxON) within 24 hours
10 | Confirmation that all required staff account set up and password reset (act on link emailed or it would expire within 24 hours) has been completed ahead of clinic day.
11 | Confirm that all clinic users are aware to receive an email from *Salesforce* and act on resetting password for their account before clinic day.
12 | Has the clinic staff been trained on privacy and clinical guidance (as required)
13 | Has the clinic staff been trained on COVAX
| Dry runs | Done
1 | Confirm with PHS that setup of hardware/connectivity and access to the COVAXon system has been completed and there are no issues
2 | Has a Dry Run been completed

## Non-Clinic (LTHCH,RH) Checklist
Readiness Check list
| Logistics | Done
1 | What administration model are you using (site staff immunization of Public Health Staff)
2 | Have you communicated to staff as to what is expected
3 | Have you prepared a schedule for vaccine administration for first dose, second dose?
4 | Have the appropriate consent for service, data collection, communication (email/SMS/other) been obtained by resident or their authorized delegate
5 | Have the appropriate assessments been conducted (vaccine product, COVID) as per clinical guidance
6 | Is the resident's health card available
7 | Do you have enough inventory for your planned immunization schedule (1st and 2nd dose)
8 | Will you be using technology or paper to record immunization event (if paper go to Paper Section only)
9 | Have you completed the templates for users (of system) and clinets (residents) - and have you securely sent to ministry and recevied confirmation
10 | Have you ensured staff participating in vaccine administration have a mobile phone and an organization email account (and know their password ahead of time) - for the 2-Factor Authentication
11 | Have you informed all staff participating in the vaccine administration to complete their SalesForce password reset ahead of first day of vaccine administration (as password expires in 24 hours)
12 | Do you have a process for new residents arriving after this wave of immunizations
| Technology | Done
1 | Have all your staff participating in the vaccine administration completed your training on the COVAxON system
2 | Does your laptop/desktop equipment meet the required specifications and have they been turned on, powered and has the user logged onto device
3 | Do you have internet access and has it been tested
4 | Do you have printers and are they connected to support printing of receipts
5 | Have you recorded your received inventory with the correct product and lot #
6 | Do you have enough consent paper forms printed to support consent process (if not available with the technology)
7 | Do you have enough AEFI forms printed
| Paper (Note: Inventory must be maintained in the system) | Done
1 | Is the process in place to collect the paper copies and record the results from the paper copies into the system
2 | Do you have enough consent paper forms printed to record immunization data
3 | Do you have enough receipts printed to provide to client's file
4 | Do you have enough AEFI forms printed
| Materials Required Daily | Done
1 | Print out AEFI forms and ensure forms are available in AEFI monitoring room
2 | Print out consent forms/ receipt form for backup and ensure printed forms/receipts are in the appropriate rooms *Recommendation: print these in different colour paper which helps differentiate for patients
3 | Office supplies such as pen, paper etc…